## Slide 1
RDE bootcamp | workshop rundown
Day 2: the full-day RDE pod simulation hackathon
Turn the case into a qualified RDE opportunity, prove the highest-value slice, and pitch a 90-day Rapid Reinvention engagement.
Today's rhythm
Frame and qualify
Prototype in three sprints
Pitch the investment case
Day 1 introduces the RDE playbook and closes with the case briefing, so Day 2 starts immediately in execution mode.

## Slide 2
How Day 2 starts
02
Teams arrive ready to execute
Day 1 hands off everything teams need; Day 2 opens straight into Envision mode.
Day 1 close handoff
- The case brief
- Sample data
- Judging rubric
- Team assignments
- Day 2 challenge statement
Ask teams not to build overnight, but to arrive with clarifying questions and initial hypotheses.
Day 2 opening message
You already have the case. Today starts as if Envision has begun: your job is to turn the case into a qualified RDE opportunity, prove the highest-value slice, and convince the sponsor this can become a 90-day Rapid Reinvention engagement.

## Slide 3
Full-day rundown
03
Morning: frame, qualify, and start to prove
09:00-12:30 | the first two blocks are time-boxed to 30 minutes - make fast, defensible choices.
Time | Activity | RDE playbook simulation | Output
09:00-09:15 | Day 2 launch, rules, scoring, team setup | Pod mobilization | Team roles, working agreement
09:15-09:45 | Problem framing and focus selection | Deal qualification + Envision | Chosen use-case slice, problem statement, success criteria
09:45-10:15 | Value hypothesis and MVP definition | Envision value hypothesis + Go / No-Go readiness | Value metric, ROI logic, MVP boundary
10:15-11:00 | Target process and solution design | Process reinvention + solution concept | Future-state workflow, human-in-loop design, architecture sketch
11:00-11:15 | Sponsor checkpoint 1 | Envision decision checkpoint | Confirmed / narrowed scope
11:15-12:30 | Prototype Sprint 1 | Rapid Reinvention - PROVE | First working slice on sample data

## Slide 4
Full-day rundown
04
Afternoon: build, package, and pitch
12:30-17:30 | working lunch keeps part of the pod moving while the build continues.
Time | Activity | RDE playbook simulation | Output
12:30-13:30 | Working lunch / build continues | Prove continuation | Data issues, prototype backlog
13:30-14:30 | Prototype Sprint 2 | Rapid Reinvention - PROVE to BUILD | Demoable prototype, initial edge cases
14:30-14:45 | Sponsor checkpoint 2 | Stage gate: "Can this fly?" | Feedback, risks, build cuts
14:45-15:45 | Prototype Sprint 3 | Rapid Reinvention - BUILD | Improved workflow, controls, exception handling
15:45-16:10 | Go-live and scale packaging | Rapid Reinvention - DELIVER + Scale-Up | Go-live assumptions, support model, Day-91 roadmap
16:10-16:25 | Final pitch prep | Executive showcase | Final demo story and slides
16:25-17:20 | Final presentations | Sponsor investment decision | Demo + value case + 90-day delivery story
17:20-17:30 | Judging and awards | Go / No-Go closeout | Winner and key takeaways

## Slide 5
Expected outputs
05
What each team finishes Day 2 with
A full RDE submission spans design, proof, value, and the path to scale - not just a deck.
Frame and qualify
- Qualified RDE use case and problem statement
- Success criteria and value hypothesis
- Target process design
Prove and bound
- Working prototype on sample data
- MVP boundary and key assumptions
- Dependency and risk register
Ready to scale
- Go-live readiness view
- Day-91 scale-up roadmap
- Executive pitch and demo

## Slide 6
Judging criteria
06
How sponsors score the investment decision
Working proof and genuine process reinvention carry the most weight - 45% combined.
Dimension | Weight
Problem framing and RDE-fit use-case selection | 15%
Process reinvention, not just automation | 20%
Working prototype evidence | 25%
Value hypothesis and measurable business impact | 15%
Go-live readiness: data, controls, security, adoption, support | 15%
Scale-up story and executive clarity | 10%